## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, I should be able enter testimonials and access other user testimonials. | Task 1: Create testimonial page | Nick/Tim/Utsav | In Progress | 8 | 8 | 8 | 8 | 8 | 8
As a user, I should be able to access contact information and information about the team. | Task 2: Create contact page | Kate/Tim/Behrad | In-Progress | 10 | 10 | 10 | 10 | 10 | 10
As a user, I can see all of the graphic objects on my screen. | Task 3: Create pages/shapes | James/Joey | Closed | 12 | 3 | 2 | 1 | 1 | 0
As a user, I can store a shape’s properties in an external file | Task 5: Create shape vector | Behrad | Closed | 10 | 7 | 5 | 5 | 4 | 4
As a user, I can render shapes and texts and be able to move shapes around the screen | Task 6: Shape functionality | All - Shapes | In Progress | 15 | 15 | 10 | 10 | 5 | 5
As a user, I should be able to add and remove shapes via an add/remove shape form. | Task 7: Shape functionality (add/remove) | James/Joey/All | Closed | 12 | 6 | 4 | 4 | 4 | 4
As a user, I can produce a detailed list of all of my shapes. | Task 8: Shape report | James/Joey | Closed | 8 | 8 | 8 | 5 | 0 | 0
As a user, I can produce a list of the shape that have an area | Task 9: Shape report | James/Brandon | Closed | 10 | 10 | 10 | 5 | 4 | 0
As a user, I should be able to list all my shapes | Task 10: Shape report | Joey/Brandon | Closed | 12 | 12 | 12 | 10 | 3 | 0
As a user, I should be able to save my canvas. | Task 11: Save to output file | James | Closed | 12 | 12 | 12 | 10 | 4 | 0
Sprint Goal
| Total |  |  | 109 | 91 | 81 | 68 | 43 | 31 | Finish most shape functionality, and UI.