## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, I should be able enter testimonials and access other user testimonials. | Task 1: Create testimonial page | Nick/Tim/Utsav | Closed | 8 | 8 | 8 | 3 | 1 | 0
As a user, I should be able to access contact information and information about the team. | Task 2: Create contact page | Kate/Tim/Behrad | Closed | 10 | 10 | 5 | 5 | 2 | 0
As a user, I can store a shape’s properties in an external file | Task 3: Test/functionality | Brandon | Closed | 4 | 2 | 0 | 0 | 0 | 0
As a user, I can render shapes and texts and be able to move shapes around the screen | Task 4: Move/edit | James/Joey | Closed | 5 | 5 | 5 | 5 | 2 | 0
As a user, I should be able to add and remove shapes via an add/remove shape form. | Task 5: Shape functionality (all shapes) | James/Joey/All | Closed | 4 | 2 | 0 | 0 | 0 | 0
| Total |  |  | 31 | 27 | 18 | 13 | 5 | 0
Sprint Goal
Finish project