## Sheet1
DATE | USER STORY | TASKS | TASK-OWNERS |  | DONE
10.2 | Misc. | - git tutorial, qt download | All |  | - Complete user stories
11.5 | 5 - Render Shapes | - move shapes, text | Ahazz, Nick |  | - Download QT
| 6 - Add/remove | - build shapes base class/inheritance | Kate, Tim, Ahazz | Utsav | - Complete Git tutorial
| 9 - List of Shapes | - build vector class to store shapes | Behrad
| Misc. | - build log-in screen | James, Joey
11.12 | 5 - Inherited Shapes | - ellipse | Nick |  | - Log-in screen
|  | - line | Behrad |  | - Vector class
|  | - polyline | Kate
|  | - text | Utsav
|  | - polygon | Tim
|  | - rectangle | Brandon
| 10 - File parsing | - implement file parsing | James, Joey
| Misc. | - test vector class | Behrad, James
11.12 | 5 - Inherited Shapes | - polyline | Kate |  | - Most shapes done
|  | - polygon | Tim |  | - Shapes on screen
| 10 - File parsing | - implement file parsing | James, Joey
| 2 - Contact Page | - contact page | Behrad, Nick
| 1 - Contact Page | - testimonials | Utsav, Brandon
| Misc. | - start UML | Kate